## PPP Contracts
Project Title | Contract Duration | Sign of contract | Expected Date of start of Operation (under contract) | Actual Delivery Date | Project Status | Type of project / Payments from the State | Total Project Cost (mn euros) | Senior Long Term Debt Facility (million euros) | Equity (million euros) | VAT Facility (million euros) | State Financial Contribution during Construction (million euros) | Source of State Financial Contribution | Senior Lenders | SPV Sponsors | VAT Provider | Grantor | Annual Availability Payments In Operational Period (mn euros) |  | Annual Availability Payments In Operational Period - 2011 | Annual Availability Payments In Operational Period - 2012 | Annual Availability Payments In Operational Period - 2013 |  |  | Annual Availability Payments In Operational Period - 2014 | Annual Availability Payments In Operational Period - 2015 | Annual Availability Payments In Operational Period - 2016 | Annual Availability Payments In Operational Period - 2017 | Annual Availability Payments In Operational Period -2018 | Annual Availability Payments In Operational Period - 2019 | Annual Availability Payments In Operational Period - 2020 | Annual Availability Payments In Operational Period - 2021 | Annual Availability Payments In Operational Period - 2022 | Annual Availability Payments In Operational Period -2023 | Annual Availability Payments In Operational Period -2024
Design, build, financing, maintenance and facilities management of 7 fire station buildings | 25 years (23 years, 2 years construction) | 2009-04-01 | 2011-04-01 | Gradually, 2011 - Sep 2014 | In Operation | Availability Payments from PIB | 25.9 | 18.8 | 3.3 | 3.8 | - | - | EIB - Eurobank | Fire Brigades Partnership S.A. (Gantzoulas S.A. 100%) | Eurobank | School Buildings Organisation SA | 2.6 | Under Contract | 1.9521 | 2.798 | 2.8124 |  |  | 2.8 | 2.8 | 2.8 | 2.8 | 2.8 | 2.9 | 2.9 | 2.9 | 3 | 3 | 3
[18 empty] | Actual payments | 0.011 | 0.15942 | 1.7355 | Total Actual Payments | 1.9059
[18 empty] | Savings (due to late delivery/performance deductions) | 1.9411 | 2.6386 | 1.0769 | Total Actual Savings | 5.6566
Design, financing, construction and facility management of 14 school buildings in the region of Attica | 27 years (25 years operation, 2 years construction) | 2014-04-01 | 2016-04-01 | - | Under Construction | Availability Payments from PIB | 58 | 38.2 | 10.1 | 9.7 | - | - | EIB – National Bank of Greece (JESSICA) | Attica Schools S.A. (ATESE S.A. 100%) | Alpha Bank | School Buildings Organisation SA | 6.8 | - | - |  |  | - | - | - | - | 5.2518 | 7.2948 | 7.3573 | 7.421 | 7.5066 | 7.5524 | 7.62 | 7.689 | 7.7807
Design, financing, construction and facility management of 10 school buildings in the region of Attica | 27 years (25 years operation, 2 years construction) | 2014-05-01 | 2016-05-01 | - | Under Construction | Availability Payments from PIB | 52 | 33.4 | 9.9 | 8.7 | - | - | EIB – National Bank of Greece (JESSICA) | JPA Attica Schools Construction and Management (J&P – AVAX 100%) | Alpha Bank | School Buildings Organisation SA | 5.9 | - | - | - | - | - | - | - | - | 4.0571 | 6.3012 | 6.3552 | 6.4102 | 6.4841 | 6.5237 | 6.5821 | 6.6417 | 6.7209
Attica Urban Transportation-Telematics System | 12 years (10.5 years operation, 18 months construction) | 2014-06-30 | 2016-01-01 | - | Under Construction | Availability Payments from PIB | 19.4 | 6.7 | 5.9 | 1.5 | 5.3 | NSRF (ESPA) | National Bank of Greece (commercial lender and JESSICA funds provider) | Advanced Transport Telematics (INTRASOFT INTERNATIONAL - INTRAKAT 50%-50%) | National Bank of Greece | Athens Urban Transport Organisation | 4.3 | - | - | - | - | - | - | - | - | 4.4635 | 4.5009 | 4.5391 | 4.578 | 4.6177 | 4.6582 | 4.6995 | 4.7416 | 4.7846
[6 empty] | SUM | 155.3 | 97.1 | 29.2 | 23.7 | 5.3 | [5 empty] | 19.6 | [6 empty] | 2.8 | 2.8 | 16.5723 | 20.8969 | 21.0515 | 21.3093 | 21.5084 | 21.6343 | 21.9017 | 22.0724 | 22.2862
PPP Projects under PPP Law 3389/2005
PIB: | Public Investment Budget
Guarantees/ contingent liabilities
Project Title | Amendments to the signed contract | Guarantee to creditors on partner's borrowing | Guarantee to partner on debt repayment | Guarantee to partner on minimum return on equity | Guarantee to partner on minimum revenue level | Government commitment that it will repay the debt of the partner if the latter has not sufficient resources for that (or in the event of problems with short-term liquidity) | Guarantee against the impact of an increase in prices of production factors | Guarantee against unforeseen technical obsolescence | Guarantee against unfavourable macro-economic trends | Guarantee on cost of refinancing | Other type of guarantee (specify in comments)
Design, build, financing, maintenance and facilities management of 7 fire station buildings | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO
Design, financing, construction and facility management of 14 school buildings in the region of Attica | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO
Design, financing, construction and facility management of 10 school buildings in the region of Attica | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO
Attica Urban Transportation-Telematics System | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO